## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2025-03-25
Group Number |  | 13
Participant 1 |  | Bajrektarevic Minea
Participant 2 |  | Harich Franziska
Participant 3 |  | Kouhnaward Samir
Participant 4 |  | Mehmedovic Ensar
Participant 5 |  | Scheder Marcel
Mentor |  | Martin Docsek
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Landing Page | 5 | 6 | 1 | 1 |  | Parent Issue für ID. 8-11
7 | Impressum und FAQ | 2 | 1.25 | -0.75 | 1 |  | Parent Issue für ID. 12 & 21
8 | Ordnerstruktur anlegen | 0.5 | 0.5 | 0 | 1
9 | index.php | 0.5 | 0.5 | 0 | 1
10 | home.php | 2 | 3 | 1 | 1
11 | Header, footer & navbar | 2 | 2 | 0 | 1
12 | faq | 1 | 0.5 | -0.5 | 1
20 | Projekt anlegen github | 1 | 2 | 1 | 1 |  | Definitiv etwas verschätzt, wie lange es dauert, aus einer handschriftlichen Liste alle Tasks abzutippen und alle erforderlichen Felder dabei auszufüllen
21 | Impressum | 1 | 0.75 | -0.25 | 1
9 |  |  |  | 1.25 | 9 | 0
Notes:
die Req ID korrespondiert mit der Project ID im Github Project, allerdings nicht mit der Issue # im Repository
Arbeitszeit der Parent Issues wurde aus der Summe ihrer Child-Issues berechnet, und daher auch aus der Delta-Berechnung herausgenommen